Team Work Allocation

& Responsibility Matrix

ServeSmart — Smart Restaurant ERP

Version 1.1

Team: Mudassar · Prashant · Bhargwi · Nikhil

Duration: 4 Weeks  |  Companion to SRS v2.1

Date: July 2026

# Table of Contents

# 1. How the Project Is Divided

Every module is owned end-to-end by one person — the same person builds its backend (Spring Boot APIs, business logic, database interaction) and its frontend (React screens for that module).

# 2. Responsibility Matrix

| Module | Owner | Week |
| --- | --- | --- |
| Authentication & RBAC | Mudassar | 1 |
| Employee Management | Prashant | 1 |
| Customer Management | Bhargwi | 1 |
| Menu Management | Bhargwi | 1 |
| Order Management | Mudassar | 2 |
| Table Management | Prashant | 2 |
| Kitchen Dashboard | Prashant | 2 |
| Billing (GST/Split/Payments) | Mudassar | 3 |
| Inventory | Mudassar | 3 |
| Supplier | Nikhil | 3 |
| Notifications | Nikhil | 3 |
| Reports & Analytics | Nikhil | 4 |
| Customer Feedback | Bhargwi | 4 |

# 3. Task Breakdown by Person

Mudassar   Authentication · Order Management · Billing · Inventory

### Authentication & RBAC (Week 1)

Backend:

- Spring Security configuration, JWT filter chain, token generation/validation

- Refresh-token rotation and server-side revocation (15-min access / 7-day refresh)

- BCrypt password hashing, role-based access checks on every protected endpoint

- Login-attempt lockout: 5 failed attempts within 10 minutes

Frontend:

- Login page, token storage/refresh handling in the API client, route guarding by role

### Order Management (Week 2)

Backend:

- Order state machine: New → Accepted → Preparing → Ready → Served → Completed, plus Rejected/Cancelled branches

- Optimistic locking on the order entity so simultaneous waiter/chef updates don't overwrite each other

- Order-lock rule: no item removal once 'Preparing'; additions become a sub-ticket instead

- Manager-approval and reason-code requirement for any cancellation after 'Accepted'

Frontend:

- Order creation screen (multi-item, running total), order status tracker, cancellation/reason-code modal

### Billing (Week 3)

Backend:

- GST engine supporting multiple slabs per item category (5% / 12% / 18%)

- Split-bill computation (by seat or by amount) and mixed-payment reconciliation

- Invoice and receipt generation

Frontend:

- Billing screen with itemized GST breakdown, split-bill UI, payment-mode entry

### Inventory (Week 3)

Backend:

- Stock in/out, low-stock alerts, stock history

- Unit-of-measure conversion: UI accepts kg/g/L/ml/pieces, stored in one base unit per ingredient

- Expiry-based alerting at a configurable threshold (default 2 days)

Frontend:

- Stock dashboard, stock-adjustment form, low-stock/expiry alert list

Prashant   Employee Mgmt · Table Mgmt · Kitchen Dashboard

### Employee Management (Week 1)

- Backend: Add/Edit/View Employee, role assignment, soft-delete only (deactivate, never hard-delete)

- Frontend: Employee list, add/edit forms, role picker

### Table Management (Week 2)

- Backend: Add/Reserve/Free tables, reservation-overlap conflict check, table-merge for large groups

- Frontend: Floor-plan/table-grid view, reservation form, merge-table action

### Kitchen Dashboard (Week 2)

- Backend: Chef's assigned-orders queue, accept/start-cooking/mark-ready transitions, 'ingredient unavailable' flag

- Frontend: Chef's live order queue, one-tap status updates

### Additional responsibility

- Swagger annotations and shared Postman collection consolidation (Week 4)

Bhargwi   Customer Mgmt · Menu Mgmt · Customer Feedback

### Customer Management (Week 1)

- Backend: Register/search customer, order-history lookup, duplicate-phone-number detection

- Frontend: Customer search/registration screen, order-history view

### Menu Management (Week 1)

- Backend: Categories, menu items, availability toggle, pricing, image upload (JPEG/PNG, max 2 MB)

- Frontend: Menu builder/editor, category view, image upload widget

### Customer Feedback (Week 4)

- Backend: Rating (1–5) and comment tied to a completed order, aggregation by menu item and date range

- Frontend: Post-order feedback form, manager-facing feedback summary view

### Additional responsibility

- Coordinates Testing Strategy across the team in Week 4

Nikhil   Supplier · Reports & Analytics · Notifications

### Supplier (Week 3)

- Backend: Supplier records, purchase orders, purchase history

- Frontend: Supplier list, purchase-order creation and history view

### Notifications (Week 3)

- Backend: In-app notifications for order status changes, low-stock/expiry alerts, cancellation/rejection events — scoped by role

- Frontend: Notification bell/list component, role-filtered feed

### Reports & Analytics (Week 4)

- Backend: Daily/Monthly Sales, Inventory Report, Top Selling Items, Chef Performance

- Frontend: Report dashboards with date-range filters and export

### Additional responsibility

- Owns Environment & Deployment: three environments, CI, staging deployment

# 4. Dependencies & Handoffs

| Depends On | Needed By | What's Needed |
| --- | --- | --- |
| Authentication (Mudassar) | Every other module | Role-based access control must exist before other modules can enforce it — priority in the first days of Week 1 |
| Menu Management (Bhargwi) | Order Management (Mudassar) | Menu items must exist before orders can reference them |
| Table Management (Prashant) | Order Management (Mudassar) | Table entity must exist before an order can be tied to a table |
| Customer Management (Bhargwi) | Order Management (Mudassar) | Customer lookup must exist before orders can attach a customer |
| Order Management (Mudassar) | Kitchen Dashboard (Prashant) | Order and order-item entities must be in place before the chef queue can consume them |
| Order Management (Mudassar) | Billing (Mudassar) | A completed order is required before an invoice can be generated |
| Inventory (Mudassar) | Kitchen Dashboard (Prashant) | 'Ingredient unavailable' flag needs an inventory endpoint — stub in Week 2, wire in the real endpoint once delivered in Week 3 |
| Order + Billing + Inventory | Reports & Analytics (Nikhil) | Reports read from data these modules produce — build reports last, in Week 4 |

# 5. Collaboration Ground Rules

- One feature branch per module (e.g., feature/order-management), merged via pull request with at least one review before merge

- Daily 10–15 minute sync to flag blockers, especially around the dependencies in Section 4

- Shared Postman collection and Swagger docs are updated by whoever adds an endpoint, not batched to the end

- If a module owner finishes early, help on whichever module is behind schedule rather than starting a new one